## Summary
ISO 27701:2025 Transition Checklist
Set the Status column on the Checklist sheet. This summary updates on its own.
Certificate deadline: 31 October 2028. Confirm your certification body's own dates.
Phase | Steps | Done | In progress | Not started | Not applicable | % complete
1. Plan the transition
2. Run the gap analysis
3. Update the management system
4. Rebuild controls and the SoA
5. Get audit ready
Total
Free from nank.ai · https://www.nank.ai/templates-and-tools/iso-27701-2025-transition-checklist/

## Checklist
Phase | Step | Action | Evidence to keep | Reference | Standalone PIMS | Status | Owner | Target date | Notes
1. Plan the transition | 1.1 | Get a licensed copy of ISO/IEC 27701:2025 for the people doing the transition work. | Purchase record or licence for the standard. | ISO/IEC 27701:2025 |  | Not started
1. Plan the transition | 1.2 | Confirm that your certification body is accredited for ISO/IEC 27701:2025 audits, and ask for its transition deadline and audit options. | Written confirmation or the certification body's transition notice. | ISO/IEC 27706:2025 |  | Not started
1. Plan the transition | 1.3 | Book the transition audit with a surveillance visit, a recertification visit or a separate visit, well before 31 October 2028. | Confirmed audit date in writing. | Transition deadline |  | Not started
1. Plan the transition | 1.4 | Name a transition owner, set a project plan with dates, and brief top management on the scope and effort. | Project plan and the briefing record or minutes. | Clause 5 |  | Not started
1. Plan the transition | 1.5 | Decide whether the PIMS stays integrated with your ISO 27001 ISMS or runs on its own. | Documented decision with the reasons. | Clause 4.3 |  | Not started
1. Plan the transition | 1.6 | If the PIMS will run without an ISMS, plan for the risk process, internal audit, document control and security controls the ISMS used to supply. | Gap list for the work the ISMS covered before. | Clauses 6 to 10, Table A.3 | Critical | Not started
2. Run the gap analysis | 2.1 | Map every 2019 requirement and control you apply to its 2025 home, using the correspondence in Annex F. | Mapping table from 2019 references to 2025 references. | Annex F |  | Not started
2. Run the gap analysis | 2.2 | Confirm where you act as a PII controller, a PII processor, or both. That decides whether Table A.1, Table A.2 or both apply. | Processing inventory showing your role for each processing activity. | Tables A.1 and A.2 |  | Not started
2. Run the gap analysis | 2.3 | Review and document the PIMS scope. Under the 2025 edition it no longer has to match your ISMS scope. | Updated PIMS scope statement. | Clause 4.3 |  | Not started
2. Run the gap analysis | 2.4 | Record each gap with an owner, a target date and the evidence you will need. | Gap register with owners and dates. | Clause 6 |  | Not started
3. Update the management system | 3.1 | Update the context of the PIMS: internal and external issues, interested parties, how you process PII, and the privacy laws that apply. | Context and interested parties register. | Clauses 4.1 and 4.2 |  | Not started
3. Update the management system | 3.2 | Decide whether climate change is a relevant issue for the PIMS and record the decision. | Context register entry showing the climate change decision. | Clause 4.1 |  | Not started
3. Update the management system | 3.3 | Update the privacy policy and confirm top management's roles and responsibilities for privacy. | Approved privacy policy and assigned PIMS roles. | Clause 5 |  | Not started
3. Update the management system | 3.4 | Run a privacy risk assessment that covers risk to the people whose PII you process, not only risk to the business. Update the treatment plan. | Privacy risk assessment and risk treatment plan. | Clause 6.1 |  | Not started
3. Update the management system | 3.5 | Set measurable privacy objectives with owners and plans to reach them. | Privacy objectives with owners and targets. | Clause 6.2 |  | Not started
3. Update the management system | 3.6 | Confirm competence, awareness, communication and document control cover the PIMS on its own terms. | Training records, communication plan and document control procedure. | Clause 7 |  | Not started
3. Update the management system | 3.7 | Put the risk treatment plan into operation and keep records that show it is working. | Operational records for the treatments in the plan. | Clause 8 |  | Not started
3. Update the management system | 3.8 | Update monitoring, internal audit and management review so they cover the 2025 requirements. | Updated audit programme and management review agenda. | Clause 9 |  | Not started
3. Update the management system | 3.9 | Confirm the nonconformity and corrective action process covers the PIMS. | Corrective action procedure and log. | Clause 10 |  | Not started
4. Rebuild controls and the SoA | 4.1 | Rebuild the Statement of Applicability on Tables A.1, A.2 and A.3, with a reason for each control you include or exclude and its status. | Statement of Applicability built on the 2025 tables. | Annex A |  | Not started
4. Rebuild controls and the SoA | 4.2 | Implement and check the security controls in Table A.3. If you hold ISO 27001, map them to your ISO 27001 Annex A controls so one piece of evidence serves both. | Table A.3 control evidence, or a mapping to ISO 27001 Annex A. | Table A.3 | Critical | Not started
4. Rebuild controls and the SoA | 4.3 | Use the Annex B guidance to check how each applicable control is implemented. | Control implementation notes referencing Annex B. | Annex B |  | Not started
4. Rebuild controls and the SoA | 4.4 | Update policies and procedures that cite 2019 clause or annex numbers. In 2019, Annex B held the processor controls. In 2025 it holds guidance. | Document register showing updated references. | Annex B |  | Not started
4. Rebuild controls and the SoA | 4.5 | Check the GDPR mapping in Annex D. Build your own mapping for PIPEDA, Quebec Law 25, HIPAA or US state privacy laws where they apply. | Legal mapping for each privacy law in scope. | Annex D |  | Not started
4. Rebuild controls and the SoA | 4.6 | If you are a public cloud PII processor, use Annex E to trace your controls to ISO/IEC 27018. | Mapping from your controls to ISO/IEC 27018. | Annex E |  | Not started
4. Rebuild controls and the SoA | 4.7 | Update contracts, data processing agreements and trust pages that name the 2019 edition, ready for the new certificate. | List of customer-facing documents to update after certification. | Customer commitments |  | Not started
5. Get audit ready | 5.1 | Train the people who run the PIMS on what changed and what it means for their work. | Training attendance records. | Clause 7.2 |  | Not started
5. Get audit ready | 5.2 | Run an internal audit against the 2025 edition across the full PIMS scope. | Internal audit report against ISO/IEC 27701:2025. | Clause 9.2 |  | Not started
5. Get audit ready | 5.3 | Hold a management review that covers the transition, the audit results and the privacy objectives. | Management review minutes. | Clause 9.3 |  | Not started
5. Get audit ready | 5.4 | Close or plan corrective action for every nonconformity from the internal audit. | Corrective action records. | Clause 10 |  | Not started
5. Get audit ready | 5.5 | Prepare the evidence pack: scope, Statement of Applicability, risk assessment, Annex F mapping, internal audit report and management review minutes. | Evidence pack ready to share with the auditor. | Audit preparation |  | Not started
5. Get audit ready | 5.6 | Complete the transition audit, close any findings within the certification body's deadline, and receive the 2025 certificate. | ISO/IEC 27701:2025 certificate. | Transition audit |  | Not started